## Organisation
ARAS DENİZ İNŞAAT A.Ş.
Project Manager Umut Karakaya
Admin Chief (1)
Construction Manager Turgay Yıldız
Captains
Seamen
ARAS DENİZ İNŞAAT A.Ş.
Survey Chief Yigit
Surveyor
Site Engineer (2)
Cagrı
Admin Personnel (1)
Electrician (1)
Formen (2) Ertan Turt, Kırkayak
HSE Engineer (2)
Technical Office Engineer Özgül
PickUp Driver for Testing Recep
Projects Coordinator Niyazi Deniz
QC Engineer OKAN

## 1.Cover
PROJECT :
QUOTATION TO TENDER
FOR Project
Price Breakdown
1
ARAS DENİZ İNŞAAT A.Ş.

## 2.Subcontract Price Summary O1
Doc. No: FR.SAT.07-A Date of Issue : 30.10.2017 Rev. Date : .. Rev. No : 01
Price Summary
■ Project : |  |  | [Currency :USD/EURO]
Item No. | Description | Amount | Remarks
0. | Mobilisation
'0 | Mobilisation | 1133333.3333 |  | Section 9*(2/3)
1. | Direct |  |  | Running Cost
1.1 | Direct Material | 0 |  | Construction Materials
1.2 | Direct Equipment | 1072500 |  | Construction Equipment | Mark Up | ARAS | TAŞARON | YAKIT | MALZEME
1.3 | Direct Labor | 487500 |  | Rate*1 | Genel Gider ve Merkez Payı | 3% | 2% | 2% | 2%
1.4 | Direct Consumables | 1135082 |  | Diesel, Lube and water | Teminatlar | 0.2% | 0.2% | 0.2% | 0.2%
[5 empty] | Finasman | 0% | 0.5% | 1% | 0%
2. | Indirect |  |  | Running Cost | Enflasyon | 0% | 0% | 1% | 0%
2.1 | Site Management&Staff | 0 |  | Engineer ect*1 | QHSE Cost | 0%
2.2 | Temporary Facilities | 0 |  |  | SSK | 0% | 0% | 0% | 0%
2.3 | Indirect Consumables | 0 |  | Site Office, Accomodation ect | Risk/Fire | 3% | 2% | 0% | 1%
[5 empty] | Kar/Zarar | 10% | 8% | 6% | 6%
3. | Environmental Monitoring | 0 |  |  | Gelir Vergisi | 5% | 1% | 1% | 1%
4. | Permit process | 0 |  |  | Sigorta | 0% | 0% | 0% | 0%
4.1 | Consulting for permission | 0 |  |  | Damga Vergisi ve Noter | 1.2% | 1.2% | 1.2% | 1.2%
4.2 | Any extra charge for permit | 0 |  |  | Stopaj | 0%
[5 empty] | TOPLAM | 22.4% | 14.9% | 12.4% | 11.4%
5. | Demobilisation
5 | Demobilisation | 566666.6667 |  | Section 9*(1/3) | Markup-Çarpanı | 1.289 | 1.175 | 1.142 | 1.129
6 | Overheads and Profits | [7 empty] | 0.129
6.1 | Overheads and Profits | 138352.5 |  | Approximately*1,289
|  |  |  | 20.25 |  | 5843597.0705
| TOTAL | 4533434.5 |  |  |  | 23000
■ Terms and Conditions | [5 empty] | 26450
28000
207.4074
238.5185
| Satıs Fiyatı | 4992700 | Yuzde
| Net Kar | 459265.5 | 0.091987
| Amortisman | 1402500 | 0.28091

## 2.BOQ
| ■ Project : GANA Project | [6 empty] | [Currency : USD]
| No. | Description | Spec | Unit | Qty | Subcontractor |  | Remarks
[6 empty] | Rate | Amount
| 1.A. | Mobilization/Demobilization
|  | Mobilization |  | LS | 1 | 1133333.3333 | 1133333.3333
|  | Demobilization |  | LS | 1 | 566666.6667 | 566666.6667
Ply | [6 empty] | 0
| 1.B.1.1. | Procurument |  |  |  |  | 0
|  | Supply of Inflated Buoyancy Bags |  | piece | 350 | 1500 | 525000
|  | Supply of Mooring Blocks |  | piece | 8 | 4400 | 35200 | [9 empty] | 16
| 1.B.1.2 | Offshore Works |  |  |  |  | 0
|  | Installation of Carbon Steel Pipe (24'') |  | m | 1920 | 1250 | 2400000
|  | Installation of Concrete Mattresses(6*3 m) |  | piece | 700 | 475 | 332500
0
|  | Total Amount |  |  |  |  | 4992700
Note)
1. All items on above BOQ is subject to change in accordance with Contractor's requirement.
2. Unit Price of All Equipment fuel shall be defined explicitly
| 1) Liter of Diesel |  | 1.109 | EUR/Liter
| 2) Liter of Marine Diesel |  | 0.467 | EUR/Liter |  |  |  |  | 전체 | 112 | 121.3 |  |  |  |  | 13585.6
| 3. Subcontractor shall quote the unit price and quantity at above BOQ format. | [7 empty] | Zone1 | 75.6 | 84.9 |  |  |  |  | 6418.44
| 4. In case of discrepancy in Tender Document, Quantity in the BOQ shall prevail. | [7 empty] | Zone2 | [6 empty] | 7167.16
[9 empty] | Zone3 | 5 | 12 | 2 | 120 | 155 | 4 | 620
[10 empty] | 5 | 7 |  | 35

## Schedule
No. | Description | Qty
|  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7
|  |  | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th
Mobilization |  | 1 | bar: 1 1st to 2 4th
Pulling Pipe duringWelding |  | 1 | bar: 3 1st to 5 4th
Sinking Pipe |  | 1 | bar: 6 1st
İnstallation Of Concrete Matresses |  | 1 | bar: 6 2nd to 7 2nd

## 5.Manpower
Direct Manpower Mobilization Plan |  | TOTAL
■ Project :
No. | Craft or Employee | 2018 | [11 empty] | TOTAL | Labor |  | Remarks | TOTAL | Consumption |  | TOTAL
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Men-Month | Rate | Amount |  | Set-Month | Accomodation | Food | Accomodation | Food
1. | INDIRECT LABOR | [21 empty] | SSK | NET | INDIRECT LABOR
| Project Manager | 2018 1: 1; 2018 2: 1; 2018 3: 1; 2018 4: 1; 2018 5: 1; 2018 6: 1; 2018 7: 0.5 | 6.5 | 8500 | 55250 |  | 6.5 | 0 | 0 | 0 | 0 | 39610 | 29340.7407 | Project Manager
| Site Chief | 2018 1: 1; 2018 2: 1; 2018 3: 1; 2018 4: 1; 2018 5: 1; 2018 6: 1; 2018 7: 0.5 | 6.5 | 6500 | 42250 |  | 6.5 | 0 | 0 | 0 | 0 | 30290 | 22437.037 | Site Chief
| Site Engineer | 2018 1: 1; 2018 2: 1; 2018 3: 1; 2018 4: 1; 2018 5: 1; 2018 6: 1; 2018 7: 0.5 | 6.5 | 4500 | 29250 |  | 6.5 | 0 | 0 | 0 | 0 | 20970 | 15533.3333 | Site Engineer
| Technical Office Chief | 2018 1: 1; 2018 2: 1; 2018 3: 1; 2018 4: 1; 2018 5: 1; 2018 6: 1; 2018 7: 0.5 | 6.5 | 5500 | 35750 |  | 6.5 | 0 | 0 | 0 | 0 | 25630 | 18985.1852 | Technical Office Chief
[20 empty] | 0 |  |  |  |  | 0
2. | DIRECT LABOR | [23 empty] | DIRECT LABOR
| Formen | 2018 1: 2; 2018 2: 2; 2018 3: 2; 2018 4: 2; 2018 5: 2; 2018 6: 2; 2018 7: 1 | 13 | 3000 | 39000 |  | 13 | 0 | 0 | 0 | 0 | 13980 | 10355.5556 | Formen
| Tug Boat | 2018 1: 10; 2018 2: 10; 2018 3: 10; 2018 4: 10; 2018 5: 10; 2018 6: 10; 2018 7: 5 | 65 | 2500 | 162500 |  | 65 | 0 | 0 | 0 | 0 | 11650 | 8629.6296 | Tug Boat
| Floating Crane | 2018 1: 6; 2018 2: 6; 2018 3: 6; 2018 4: 6; 2018 5: 6; 2018 6: 6; 2018 7: 3 | 39 | 2000 | 78000 |  | 39 | 0 | 0 | 0 | 0 | 9320 | 6903.7037 | Floating Crane
| service boat | 2018 1: 4; 2018 2: 4; 2018 3: 4; 2018 4: 4; 2018 5: 4; 2018 6: 4; 2018 7: 2 | 26 | 1750 | 45500 |  | 26 | 0 | 0 | 0 | 0 | 8155 | 6040.7407 | service boat
| TOTAL | [14 empty] | 487500 |  |  |  |  | 0 | 0

## 6.Equipment
Construction Equipment Mobilization Plan
■ Project : |  |  |  | Mobilization Plan by Month | [10 empty] | [Currency : USD] | [8 empty] | [Currency : USD]
TOTAL WORK
No. | Equipment Name | Capacity/Spec | Qwn or Rental | 2018 | [7 empty] | TOTAL | Equipment |  | Remarks | TOTAL | Diesel | Diesel | Lube | Insurance | Maintenance | Total |  | Remarks
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | Set-Month | Rate | Amount |  | Set-Month | Ton | Consumption | EUR | EUR | EUR | Rate | Amount
1 | Tug Boat | 5150Hp | Own | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 |  | 6.5 | 90000 | 585000 |  | 6.5 | 150 | 96000 | 20000 | 10000 | 0 | 126000 | 819000
| Floating Crane | 80t | Own | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 |  | 6.5 | 60000 | 390000 |  | 6.5 | 15 | 14580 | 10000 | 5000 | 0 | 29580 | 192270
| Service Boat | 300Hp | Own | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 |  | 6.5 | 15000 | 97500 |  | 6.5 | 9 | 6048 | 10000 | 3000 | 0 | 19048 | 123812
| TOTAL | [12 empty] | 1072500 | [8 empty] | 1135082

## 7.Subcontractor
Doc. No: FR.SAT.07-F Date of Issue : 30.10.2017 Rev. Date : .. Rev. No : 01
Subcontractor Cost Summary
Work Description | Unit | Qty. | Unit Price (Euro) | Total (Euro)
TOTAL: |  |  |  | 0

## 8. Material
Doc. No: FR.SAT.07-G Date of Issue : 30.10.2017 Rev. Date : .. Rev. No : 01
Material Cost Summary
Material Description | Unit | Qty. | Unit Price (Euro) | Total (Euro) | Unit Price (Tl) m3 | Unit Price (Tl) ton
Construction Material |  |  |  | 0
0
0
TOTAL: |  |  |  | 0
Indirect Material |  |  |  | 0
Bez Sapan Vs… |  |  |  | 0
Oksijen |  |  |  | 0
Kaynak vs… |  |  |  | 0
0
TOTAL: |  |  |  | 0
GRAND TOTAL: |  |  |  | 0

## 9. Mob-Demob Masrafları
Doc. No: FR.SAT.07-H Date of Issue : 30.10.2017 Rev. Date : .. Rev. No : 01
Mob-Demob Cost Summary
Material Description | Unit | Qty. | Unit Price (Euro) | Total (Euro)
Temporary Facilities Cost
Site Office | Nos | 1 | 25000 | 25000
TOTAL:
Mob-Demob Costs
DP1 Deck Cargo Ship | Nos | 1 | 12000 | 12000
Sennebogen Material Handler | Nos | 1 | 6000 | 6000
Sennebogen Crawler Crane | Nos | 1 | 6000 | 6000
Split Hopper Barge-1 | Nos | 1 | 25000 | 25000
Split Hopper Barge-2 | Nos | 1 | 25000 | 25000
Survey Boat | Nos | 1 | 1500 | 1500
Service Boat | Nos | 1 | 1500 | 1500
Underwater Leveling Equipment | Nos | 1 | 40000 | 40000
Floating Crane | Nos | 1 | 12000 | 12000
Tug Boat | Nos | 1 | 22000 | 22000
TOTAL: |  |  |  | 176000
GRAND TOTAL: |  |  |  | 176000