## 2.Subcontract Price Summary O1
Doc. No: FR.SAT.07-A Date of Issue : 30.03.2018 Rev. Date : .. Rev. No : 02
Price Summary
■ Project : |  |  | [Currency :EURO]
Item No. | Description | Amount | Remarks
0. | Mobilisation
'0 | Mobilisation | 268666.6667 | 147766.6667 | Section 9*(2/3)
1. | Direct |  |  | Running Cost
1.1 | Direct Material | 0 | 0 | Construction Materials
1.2 | Direct Equipment | 669375 | 368156.25 | Construction Equipment | Mark Up | ARAS | TAŞARON | YAKIT | MALZEME
1.3 | Direct Labor | 357812.5 | 196796.875 | Rate*1,35 | Genel Gider ve Merkez Payı | 3% | 0% | 2% | 2%
1.4 | Direct Consumables | 310800 | 44133.6 | Diesel, Lube and water | Teminatlar | 0.2% | 0.2% | 0.2% | 0.2%
[5 empty] | Finasman | 0.5% | 0.5% | 1% | 0.5%
2. | Indirect |  |  | Running Cost | Enflasyon | 0% | 0% | 1% | 1%
2.1 | Site Management&Staff | 594274.375 | 326850.9062 | Engineer ect*1,35 | QHSE Cost | 1%
2.2 | Temporary Facilities |  |  | Site Office, Accomodation ect | SSK | 0% | 0% | 0% | 0%
2.3 | Indirect Consumables |  |  | Car rent ect… | Risk/Fire | 5% | 2% | 0% | 1%
[5 empty] | Kar/Zarar | 15% | 8% | 6% | 6%
3. | Environmental Monitoring |  |  |  | Gelir Vergisi | 5% | 1% | 1% | 1%
4. | Permit process |  |  |  | Sigorta | 1% | 0% | 0% | 0%
4.1 | Consulting for permission |  |  |  | Damga Vergisi ve Noter | 1.2% | 1.2% | 1.2% | 1.2%
4.2 | Any extra charge for permit |  |  |  | Stopaj | 3.6%
[5 empty] | TOPLAM | 35.5% | 12.9% | 12.4% | 12.9%
5. | Demobilisation
5 | Demobilisation | 134333.3333 | 73883.3333 | Section 9*(1/3) | Markup-Çarpanı | 1.55 | 1.148 | 1.142 | 1.148
6 | Overheads and Profits |  |  |  |  | 55% | 14.8% | 14.2% | 14.8%
6.1 | Overheads and Profits | 1157587.6312 |  | Approximately*1,15
| TOTAL | 3492849.5063
■ Terms and Conditions

## 3.Schedule
Table 1: Work Schedule
Item | Description | Unit | Tot. Qua. | Daily Production | Duration | Duration | [26 empty] | REMARKS
[7 empty] | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 | 8
1 | Mobilisation of Marine Vessel | LS | 1 | 0.033333 | 30 | 1 | 0.25 | 0.25 | 0.25 | 0.25
2 | Dredging of Pipeline Trench | m3 | 24080.5 | 400 | 61 | 2 |  |  |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
3 | Sinking Pipeline | m | 500 | 71.4286 | 7 | 0.25 | [13 empty] | 0.25
4 | Backfilling of Pipeline |  |  |  | 53 | 0
4.1 | Pipe Bedding | m3 | 377.52 | 100 | 4 | 0.25 | [12 empty] | 0.25
4.2 | Native Soil | m3 | 2153.72 | 350 | 7 | 0.25 | [14 empty] | 0.25
4.3 | 30-80 mm Crushed Stone | m3 | 4228.36 | 700 | 7 | 0.25 | [15 empty] | 0.25
4.4 | 60-300 kg ROCK | m3 | 6902.44 | 500 | 14 | 0.5 | [16 empty] | 0.25 | 0.25
4.5 | Backfill | m3 | 10418.48 | 500 | 21 | 0.75 | [18 empty] | 0.25 | 0.25 | 0.25
3 | Demobilisation | no's | 1 | 0.033333 | 30 | 1 | [21 empty] | 0.25 | 0.25 | 0.25 | 0.25

## 4.Equipment
Table 2: Equipment Schedule
Item | Equipment | [20 empty] | Total Month | Monthly Price | Total Price | REMARKS
|  | 1 | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 | 7 | 8
1 | Tugboat |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  |  | 4.25 | 75000 | 318750 | Own
1 | Backhoe Dredger |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  |  | 4.25 | 100000 | 425000 | Own
2 | Split Barge-1 |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  |  | 4.25 | 20000 | 85000 | Own
3 | Split Barge-2 |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  |  | 4.25 | 20000 | 85000 | Own
4 | Survey Boat |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  |  | 4.25 | 10000 | 42500 | Own
5 | Service Boat |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  |  | 4.25 | 7500 | 31875 | Own
669375

## 5.Manpower
Table 3: Manpower Schedule
Item | Equipment | [30 empty] | REMARKS
|  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 | Total Month | Staff No | Avr.Staff Salary | Monthly Total | Total Price
Staff
1 | Project Manager | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 6.25 | 1 | 2250 | 2250 | 14062.5
2 | Construction Manager | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 6.25 | 1 | 1750 | 1750 | 10937.5
6 | Survey Chief | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 6.25 | 1 | 1750 | 1750 | 10937.5
7 | Site Engineer | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 6.25 | 2 | 1250 | 2500 | 15625
8 | Surveyor | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 6.25 | 2 | 1000 | 2000 | 12500
10 | Admin Personnel | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 6.25 | 2 | 1000 | 2000 | 12500
Labour
1 | Tugboat | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 6.25 | 8 | 1250 | 10000 | 62500
2 | Backhoe Dredger | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 6.25 | 6 | 2000 | 12000 | 75000
3 | Split Barge-1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 6.25 | 5 | 1000 | 5000 | 31250
4 | Split Barge-2 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 6.25 | 5 | 1000 | 5000 | 31250
5 | Survey Boat | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 6.25 | 2 | 1000 | 2000 | 12500
6 | Service Boat | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 6.25 | 2 | 1000 | 2000 | 12500
7 | Divers | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 6.25 | 2 | 2000 | 4000 | 25000
8 | Excavator | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 6.25 | 6 | 2500 | 15000 | 93750
9 | Roller | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 6.25 | 7 | 2500 | 17500 | 109375
[28 empty] | 9 | Total Price for Staff |  | 76562.5
[28 empty] | 43 | Total Price for Labour |  | 281250
[28 empty] | 52 | Total Workmanship |  | 357812.5

## 6.Mob-Demob
| Mob+Demob Duration | 2
Item | Equipment | Equipment Rate |  | Manpower | MGO (ton/month) | MGO (USD)
0 | Tugboat | 75000 | 150000 | 48000 | 165 | 132000
1 | Backhoe Dredger | 100000 | 200000 | 24000 |  | 0
2 | Split Barge-1 | 20000 | 40000 | 10000 | 22.5 | 18000
3 | Split Barge-2 | 20000 | 40000 | 10000 | 22.5 | 18000
4 | Survey Boat | 10000 | 20000 | 4000 |  | 0
5 | Service Boat | 7500 | 15000 | 4000 |  | 0
0
0
0
|  |  | 315000 | 52000 |  | 36000
[5 empty] | Mob Total | 403000

## 7.MGO+Lub+Insurance
Table 2: Marine construction works
Item | Equipment | [7 empty] | REMARKS
|  | Total Month | Daily MGO | Monthly MGO | MGO USD | Lub USD | Insurance | Total Price
1 | Tugboat | 4.25 | 4 | 120 | 408000 | 12000 | 6000 | 426000
1 | Backhoe Dredger | 4.25 | 1 | 30 | 102000 | 12000 | 6000 | 120000
2 | Split Barge-1 | 4.25 | 0.5 | 15 | 51000 | 12000 | 6000 | 69000 | Own
3 | Split Barge-2 | 4.25 | 0.5 | 15 | 51000 | 12000 | 6000 | 69000
4 | Survey Boat | 4.25 | 0.2 | 6 | 20400 | 4000 | 2000 | 26400
5 | Service Boat | 4.25 | 0.2 | 6 | 20400 | 4000 | 2000 | 26400
[6 empty] | 44000 | 22000 | 310800

## 8.Material
Table 2: Material List
Item | Equipment |  |  |  | REMARKS
|  | Total Amount | Unit Price | Total Price
0

## 9.Indirect
Table 2: Marine construction works
Item | Equipment |  |  |  | REMARKS
|  | Total Amount | Unit Price | Total Price
1 | Taxes (%6) | 1 | 21468.75 | 21468.75
2 | Social Security Costs (%29) | 1 | 103765.625 | 103765.625
3 | Accomandation | 52 | 2700 | 140400
4 | Work Permit Cost | 52 | 2000 | 104000
5 | Provision | 52 | 4320 | 224640
594274.375